Proposal for the Event

Soulstice Fundraising Project

Last edited on: 25/02/2026

| SECTION A - PROJECT COORDINATORS |  |  |  |  |
| --- | --- | --- | --- | --- |
| S/N | Name | Project Role | Contact | Student Email |
| 1. | Trina Tham Yanting | Souls Vice-Chairperson | 9479 9218 | trinatham001@suss.edu.sg |
| 2. | Lim Jing Xian Dorothy | Souls Dance Captain | 8723 4649 | dorothylim002@suss.edu.sg |
| 3. | Cheow Rui En (Hana) | Souls Dance Captain | 9474 2025 | recheow001@suss.edu.sg |
| 4. | Churn Jen Shi | Souls Publicity | 8331 7220 | jschurn001@suss.edu.sg |
| 5. | Chloe Lim Jiexi | Souls Welfare | 8809 3212 | chloelim005@suss.edu.sg |

| SECTION B – PROJECT DESCRIPTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| DESCRIPTION |  |  |  |  |  |
| [What is the project about? What is the project’s objective? How does your student group intend to meet these objectives? What are the activities involved in this event?] This fundraising event will be in the form of conducting open classes where SUSS students and public are able to join Soulstice members during the classes. Due to the success and high turn-up rate of 2025’s fundraising classes, we have decided to bring back this event in 2026. Before the fundraising classes start, Jagua tattoo services will also be available. These charged services will contribute to the funds collected. Prices for the Jagua tattoos are subjective according to design. Additional sessions for Jagua tattoo services will be held on other selected Wednesdays, from 4.30pm-6.00pm. Funds collected would be deposited back to Dance(x) bank account to support Soulstice’s trainings and events. Tiered Pricing: SUSS Students: $8 Public: $10 |  |  |  |  |  |
| DELIVERABLES |  |  |  |  |  |
| Venue Requirements |  |  |  |  |  |
| [Please state the venues the project will be using as well as date and time for the project.] We aim to hold our fundraising classes from February to December 2026, during our student-led sharing sessions on specific Wednesdays, 7-9pm. Fundraising Class would be held in our dance studio, NP Blk 23 Level 1 Movement Studio. However, on dates where there is a higher volume of participants, an alternative venue such as the Fish Tank may be requested for. Jagua tattoo services would be held in the Fish Tank. Previously, sessions were held at the tables at NP Blk 23 Level 1. Due to the success and feedback of previous sessions, we have decided to expand our services by making them more accessible to SUSS students. |  |  |  |  |  |
| Logistical Needs |  |  |  |  |  |
| No.; Item Name; Item Description; Estimated Cost. 1.; JBL PB Encore Essential; Dance(x) Speaker. |
| ADDITIONAL NOTES |  |  |  |  |  |
| SECTION C - PROPOSED TIMELINE |  |  |  |  |  |
| Fill for additional notes. |  |  |  |  |  |
| S/N | ACTIVITIES/EVENTS | DATE/DAY | TIME | VENUE | BUDGET (if any) |
| 1 | Publicity Campaign | Now till end of event | - | - | - |
| 2 | Open Class 1 | 04 Feb | 7-9 pm | Movement Studio | - |
| 3 | Open Class 2 | 11 Mar | 7-9 pm | Movement Studio | - |
| 4 | Open Class 3 | 29 April | 7-9 pm | Movement Studio | - |
| 5 | Jagua Tattoo Service 1 | 06 May | 4.30-6pm | Fish Tank | - |
| 6 | Jagua Tattoo Service 2 | 13 May | 4.30-6pm | Fish Tank | - |
| 7 | Jagua Tattoo Service 3 | 20 May | 4.30-6pm | Fish Tank | - |
| 8 | Jagua Tattoo Service 4 | 03 June | 4.30-6pm | Fish Tank | - |
| 9 | Open Class 4 | 10 June | 7-9 pm | Movement Studio | - |
| 10 | Jagua Tattoo Service 5 | 17 June | 4.30-6pm | Fish Tank | - |
| 11 | Jagua Tattoo Service 6 | 24 June | 4.30-6pm | Fish Tank | - |
| 12 | Jagua Tattoo Service 7 | 01 July | 4.30-6pm | Fish Tank | - |
| 13 | Open Class 5 | 08 July | 7-9 pm | Movement Studio | - |
| 14 | Jagua Tattoo Service 8 | 15 July | 4.30-6pm | Fish Tank | - |
| 15 | Jagua Tattoo Service 9 | 22 July | 4.30-6pm | Fish Tank | - |
| 16 | Jagua Tattoo Service 10 | 29 July | 4.30-6pm | Fish Tank | - |
| 17 | Open Class 6 | 05 Aug | 7-9 pm | Movement Studio | - |
| 18 | Jagua Tattoo Service 11 | 12 Aug | 4.30-6pm | Fish Tank | - |
| 19 | Jagua Tattoo Service 12 | 19 Aug | 4.30-6pm | Fish Tank | - |
| 20 | Jagua Tattoo Service 13 | 26 Aug | 4.30-6pm | Fish Tank | - |
| 21 | Open Class 7 | 02 Sep | 7-9 pm | Movement Studio | - |
| 22 | Jagua Tattoo Service 14 | 09 Sep | 4.30-6pm | Fish Tank | - |
| 23 | Jagua Tattoo Service 15 | 16 Sep | 4.30-6pm | Fish Tank | - |
| 24 | Jagua Tattoo Service 16 | 23 Sep | 4.30-6pm | Fish Tank | - |
| 25 | Open Class 8 | 30 Sep | 7-9pm | Movement Studio | - |
| 26 | Jagua Tattoo Service 17 | 07 Oct | 4.30-6pm | Fish Tank | - |
| 27 | Jagua Tattoo Service 18 | 14 Oct | 4.30-6pm | Fish Tank | - |
| 28 | Open Class 9 | 21 Oct | 7-9pm | Movement Studio | - |
| 29 | Jagua Tattoo Service 19 | 28 Oct | 4.30-6pm | Fish Tank | - |
| 30 | Open Class 10 | 02 Dec | 7-9pm | Movement Studio | - |
| 31 | Open Class 11 | 30 Dec | 7-9pm | Movement Studio | - |
| SECTION D – BUDGET PROPOSAL |  |  |  |  |  |
| [Please state in remarks the funding sources you will be using in this section. For eg, Campus Project Funding, Sports for Good Funding, etc.] Fill for additional notes. |  |  |  |  |  |
| S/N | ACTIVITY/ITEM | ESTIMATED COST | REQUESTED FUNDING FROM STL | STUDENT FUNDING (if any) | REMARKS |
| Total withdrawal: |  |  |  |  | Total Deposit from STL Funding: |
| (No Budget Required) |  |  |  |  |  |
| SECTION E – PUBLICITY PLAN |  |  |  |  |  |
| [Please provide the EDM, EDM write-up and registration link (if applicable)] We plan to post on our club’s Instagram account (@/suss.soulstice) and send a message in SUSS student life Telegram channel (once approved) to spread awareness for the event. We will also post on our Soulstice Fundraising Telegram channel. Utilising SUSS’s Qualtrics System for registration. |  |  |  |  |  |
| SECTION F – ACKNOWLEDGEMENTS |  |  |  |  |  |
| By submitting this form: - We acknowledge that we will adhere to the PDPA clauses as presented in this school link. - We acknowledge that both Committees and Staff Mentors from the Student groups are aware and support the proposed project. I, Trina Tham Yanting, Vice-Chairperson of Soulstice acknowledge that the aforementioned details in this proposal are true and that I am acting at the approval of Soulstice/Dance(X). Trina Tham Yanting, 25/02/2026 _______________________________ Signature, Name of Student Leader & Date |  |  |  |  |  |