*NOTE: This proposal should be submitted at least 8 weeks before the event day

Proposal for the Event

SensaXion Fundraiser Classes

Last edited on: 24/05/2026

| SECTION A - PROJECT COORDINATORS |  |  |  |  |
| --- | --- | --- | --- | --- |
| S/N | Name | Project Role | Contact | Student Email |
| 1. | Vaniz Pang | Vice-Chairperson | 9193 2139 | vanizpang001@suss.edu.sg |
| 2. | Lim Xin Ying | Dance Captain | 8749 6838 | xylim023@suss.edu.sg |
| 3. | Shayanne Lim | Dance Captain | 8818 6485 | shayannelim001@suss.edu.sg |
| 4. | Crystal Goh | Welfare | 9823 9120 | crystalgoh003@suss.edu.sg |
| 5. | Victoria Tan | Publicity | 9299 0469 | victoriatan001@suss.edu.sg |

| SECTION B – PROJECT DESCRIPTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| DESCRIPTION |  |  |  |  |  |
| [What is the project about? What is the project’s objective? How does your student group intend to meet these objectives? What are the activities involved in this event?] This fundraising event will be conducted in the form of open dance classes, where SUSS students and members of the public may register to participate in our training sessions. The classes will be facilitated by our own dancers. All funds collected will be deposited into the Dance(X) bank account and utilised to cover instructor fees and other activities for the rest of the year. This fundraising will also serve as an opportunity for the incoming SUSS freshmen to experience our IG’s trainings. We will promote our IG and raise awareness about our CGIG performance and recruitment. |  |  |  |  |  |
| DELIVERABLES |  |  |  |  |  |
| Venue Requirements |  |  |  |  |  |
| [Please state the venues the project will be using as well as date and time for the project.] The fundraising classes are planned to be conducted in July, and subject to availability, in September and October as well. These sessions will be held on Tuesdays and Thursdays from 7pm to 9pm. The classes will take place at NP Block 23 Movement Studio. |  |  |  |  |  |
| SECTION C - PROPOSED TIMELINE |  |  |  |  |  |
| Fill for additional notes. |  |  |  |  |  |
| S/N | ACTIVITIES/EVENTS | DATE/DAY | TIME | VENUE | BUDGET (if any) |
| 1 | Publicity | One month prior | - | - | - |
| 2 | Class 1 | 9 July (Thu) | 7pm-9pm | Movement Studio | - |
| 3 | Class 2 | 14 July (Tue) | 7pm-9pm | Movement Studio | - |
| 4 | Class 3 | 16 July (Thu) | 7pm-9pm | Movement Studio | - |
| 5 | Class 4 | 23 July (Thu) | 7pm-9pm | Movement Studio | - |
| SECTION D – BUDGET PROPOSAL |  |  |  |  |  |
| [Please state in remarks the funding sources you will be using in this section. For eg, Campus Project Funding, Sports for Good Funding, etc.] Fill for additional notes. |  |  |  |  |  |
| S/N | ACTIVITY/ITEM | ESTIMATED COST | REQUESTED FUNDING FROM STL | STUDENT FUNDING (if any) | REMARKS |
| Total withdrawal: |  |  |  |  | Total Deposit from STL Funding: |
| (No Budget Required) |  |  |  |  |  |
| SECTION E – PUBLICITY PLAN |  |  |  |  |  |
| [Please provide the EDM, EDM write-up and registration link (if applicable)] Promotional efforts will include posts on the club’s official Instagram account, as well as a message circulated through the SUSS Student Life Telegram channel, subject to approval. Registration for the event will be facilitated through SUSS’s Qualtrics system. |  |  |  |  |  |
| SECTION F – ACKNOWLEDGEMENTS |  |  |  |  |  |
| By submitting this form: - We acknowledge that we will adhere to the PDPA clauses as presented in this school link. - We acknowledge that both Committees and Staff Mentors from the Student groups are aware and support the proposed project. I, Vaniz Pang, Vice-Chairperson of SensaXion, acknowledge that the aforementioned details in this proposal are true and that I am acting at the approval of SensaXion/Dance(X). Vaniz Pang, 24/05/2026 __________________________________ Signature, Name of Student Leader & Date |  |  |  |  |  |